## Sheet1
TASK NAME | FEATURE | RESPONSIBLE | START DATE | END DATE | DURATION | STATUS | COMMENTS
SPRINT 1 | SPRINT GOAL: Create necessary frontend pages/UI elements
Feature 1 | Navigation + Search Bar for Products | Liam | 2025-10-21 | 2025-10-23 | 2 Classes | Complete | Navigation + Search Bar Completed. Search bar will need eventual backend integration for product search functionality.
Feature 2 | Banner Design + Website Icons | Thea | 2025-10-21 | 2025-10-23 | 2 Classes | Complete | Created a banner for the home page to welcome customers into the shop. Also created additional assets for the website (e.g. Genie for the Contact Us button).
Feature 3 | Contact Page (Frontend Layout + Embedded Google Form) | Jonathan | 2025-10-21 | 2025-10-23 | 2 Classes | Complete | The contact page has been completed, allowing customers to fill out a Google form to contact the company owners. In the future, this may need to be adjusted (e.g. change receiving email address or add additional fields to the form) based on client needs.
Feature 4 | About Us page implementation | Naim | 2025-10-21 | 2025-10-23 | 2 Classes | Complete | The About Us page has been completed, which will serve to tell customers about WelkinWonders values, history, etc.
SPRINT 2 | SPRINT GOAL: Implement frontend client feedback, continue frontend implementation, and begin structuring backend
Feature 1 | General Database Design: Product & User Schema; Knowledge Acquisition | Liam | 2025-10-28 | 2025-10-30 | 2 Classes | Complete | The general schema for the User and Product tables have been completed. Also began studying the Laravel framework for backend functionality (knowledge acquisition). These will eventually be integrated with Laravel to allow for products to be displayed + shopping cart functionality.
Feature 2 | Fix image issues and adding new images to the website layout | Thea | 2025-10-28 | 2025-10-30 | 2 Classes | Complete | Fixed an issue regarding the homepage banner not being properly displayed. Also added new image to the navigation bar + tab image.
Feature 3 | Shop Page (Frontend Layout + Product Card Template) | Jonathan | 2025-10-28 | 2025-10-30 | 2 Classes | Complete | Created the shop page with generic product cards which will eventually be populated with real product data from a database.
Feature 4 | Adding About Us to the homepage + Admin Page (Frontend) | Naim | 2025-10-28 | 2025-10-30 | 2 Classes | Complete | The About Us page has been moved to the home page per client feedback. Also created the Admin page which will eventually interact with the database. This includes the ability to add or remove products, update stock values, and view sales metrics.
SPRINT 3 | SPRINT GOAL: Continue working on frontend elements and begin integrating them to the Laravel framework
Feature 1 | Transition to Laravel + User Authentication | Liam | 2025-11-04 | 2025-11-06 | 2 Classes | In Progress | In the process of transitioning our frontend to the Laravel framework. Completed user authentication setup, allowing users to login to WelkinWonders. Still need to test routing to ensure proper permissions (e.g. a guest should not be able to go to the Admin dashboard).
Feature 2 | Continue cleaning up frontend elements (e.g. ensuring no overflow of elements) | Thea | 2025-11-04 | 2025-11-06 | 2 Classes | In Progress | Continued cleaning up the front end code to ensure no overflow or improper element formatting.
Feature 3 | Product Page (Frontend Layout, Generic Product Template, and Review Section) | Jonathan | 2025-11-04 | 2025-11-06 | 2 Classes | Complete | Created a generic product page template which will eventually interact with the database. Also includes a review section for customers to leave reviews. The product page will eventually integrate with Laravel to display an existing product, display and allow customer reviews, and add the item to a shopping cart.
Feature 4 | Begin transitioning Admin frontend page to Laravel framework | Naim | 2025-11-04 | 2025-11-06 | 2 Classes | In Progress | In the process of transitioning the Admin page to the Laravel framework, including adjusting frontend to the new framework, as well as integrating front end features with the database (e.g. the Products table).